## Bootcamp Roadmap
LLM Bootcamp — June 8–12, 2026 · Preparation Priority Roadmap
Prep week: Tue Jun 2 – Fri Jun 5 · Source: priority matrix + bootcamp schedule
# | Task | Description | Owner | Needed by | Priority quadrant | Why this order
TUESDAY Jun 2
One connected decision block: LangGraph scope + curriculum finalised in the same session..
1 | LangGraph / Agents / Memory AND prompt engineering fundamentals — include or drop? | Both overlap with content taught in the Agentic AI bootcamp — LangGraph/Agents with Context Engineering, and prompt engineering fundamentals with existing sessions. Including either makes Day 3 redundant for returning participants. Decide both today in the same session — this determines whether items 2 and 3 below are needed and locks Day 3 curriculum. | Radhika + Raja | Jun 2 — blocks Day 3 (Jun 10) | DO IT NOW | Root decision covering two topics. Items 2 and 3 are conditional on this. If both are dropped, the curriculum gap on Day 3 must be filled today. If either stays, confirm exactly what remains so Wednesday LangChain notebook walk-through covers the right scope.
2 | If dropped: add security & compliance session to curriculum | If LangGraph / Agents / Memory AND prompt engineering fundamentals are both dropped, decide whether security and compliance fills part of the curriculum gap on Day 3 (Jun 10). Confirm with Raja in the same Tuesday session — do not leave this open. | Radhika + Raja | Jun 2 — conditional on item 1 | DO IT NOW | Must be decided same session as item 1. If LangGraph and prompt engineering fundamentals are both going, this and item 3 are what replace them. Day 3 curriculum must be final by end of Tuesday so Wednesday prep can begin with the correct scope.
3 | If dropped: add product management lessons to curriculum | If LangGraph / Agents / Memory AND prompt engineering fundamentals are both dropped, decide whether PM lessons also fill part of the gap on Day 3 alongside or instead of security & compliance. Confirm in the same Tuesday session. | Radhika + Raja | Jun 2 — conditional on item 1 | DO IT NOW | Same session as items 1 and 2. All three decisions close together so Day 3 curriculum is fully final on Tuesday. Security/compliance and PM lessons together or separately replace the dropped content — confirm which combination works for the available time slot.
4 | Enterprise Adoption slides — review & confirm which go to Canva | Revised slides ready. One review session today to confirm which are selected. Blocks Canva production work on Wednesday. Needed for Day 1: Challenges in Enterprise Adoption (Jun 8, 11:30 AM–12:15 PM, Raja). | Radhika + Raja | Jun 2 — needed for Day 1 (Jun 8) | DO IT NOW | Low effort — slides already revised. Completing this today gives Wednesday for Canva production. If missed, Day 1 slides will not be in final Canva template.
5 | LLM Landscape deck — go / no-go | Not significantly updated in months. Decide today: ship as-is, minor edit, or rewrite. Needed for Day 1: Understanding the LLM Landscape (Jun 8, 9–11:30 AM, Raja). | Radhika + Raja | Jun 2 — needed for Day 1 (Jun 8) | DO IT NOW | Quick decision with a clear output. Day 1 opens with this session at 9 AM. If a rewrite is needed, that cannot start without deciding today.
WEDNESDAY Jun 3
Tuesday decisions locked. Day 3 curriculum is final. Independent tasks start immediately.
6 | Check & run evaluation notebooks | Notebooks shared. Check and run before Day 4: Evaluation of LLMs + Practical Exercises (Jun 11, 9 AM–12:15 PM, Raja). Will be demonstrated live to participants. Independent of all Tuesday decisions — start first thing. | Raja + Radhika | Jun 3 — needed for Day 4 (Jun 11) | DO IT NOW | Independent of Tuesday decisions. Running Wednesday gives maximum lead time if issues are found. A broken notebook cell live on Day 4 has no recovery.
7 | Walk through new LangChain notebook | Full agentic RAG pipeline on single dataset using LangChain. Covers Day 2 afternoon (Jun 9, 3:30–5 PM) and Day 3 (Jun 10). Scope is now final after Tuesday's LangGraph decision. | Radhika + Raja | Jun 3 — needed for Days 2–3 (Jun 9–10) | DO IT NEXT | Depends on Tuesday LangGraph decision (now resolved). This is the most important content task on Wednesday. Raja cannot teach the new single-dataset notebook cold.
8 | Move approved Enterprise Adoption slides to Canva | After Tuesday's review confirms which slides are selected, move into Canva template. Needed for Day 1: Challenges in Enterprise Adoption (Jun 8, 11:30 AM–12:15 PM). | Radhika | Jun 3 — needed for Day 1 (Jun 8) | DO IT NEXT | Depends on Tuesday review. Canva production is straightforward once slides are approved. Wednesday is the last safe day to complete this before the bootcamp.
THURSDAY Jun 4
Content production. Wednesday notebook walk-through must be complete. Kartik hard deadline today EOD.
9 | Revamp LangChain slide deck | Must align with new single-dataset notebook. Scope locked by LangGraph decision (Tue) and notebook walk-through (Wed). Covers Day 2 afternoon (Jun 9) and Day 3 (Jun 10): Output parsers, Document loaders, Retrievers, Chains — and LangGraph/Agents only if kept. | Radhika / team | Jun 4 — needed for Days 2–3 (Jun 9–10) | DO IT NEXT | Cannot start until Wednesday walk-through is done. Thursday is the only remaining production day. Must be complete before Friday verification.
10 | Kartik confirmation — Raja on standby as backup | Kartik (tentative) teaching Fine Tuning of LLMs — Day 4, Jun 11, 1–5 PM (4 hrs). Confirming in-person today. If he cannot attend, Raja covers. Lock backup explicitly by EOD. | Radhika | Jun 4 EOD — Day 4 (Jun 11) | DO IT NEXT | Hard deadline. If unresolved by EOD Thursday, Raja needs time to prepare a 4-hour Fine Tuning session. Do not let this slip to Friday.
11 | Verify final project fixes end-to-end | Guidelines, download, and UI fixes confirmed. Run through entire final project as a participant. Day 5: Final Project (Jun 12, 2–5 PM, Raja + Zaid). Independent — run in parallel with slide work. | Hiba / Sara | Jun 4 — needed for Day 5 (Jun 12) | DO IT NEXT | Independent of all other tasks. Running Thursday means if a problem is found there is still Friday to fix it. If found Friday there is no time.
12 | Revise Challenges in RAG-Based LLMs deck | If confirmed for Day 5: Challenges in RAG Based LLM Applications (Jun 12, 11 AM–12:15 PM, Raja). Revise deck and confirm scope and time allocation. Recording feeds self-paced video pipeline. | Radhika / team | Jun 4 — needed for Day 5 (Jun 12) | DO IT IF/WHEN THERE IS TIME | Session is on Day 5 — last day. Not a blocker for earlier days. But if teaching it, the recording quality matters for the self-paced pipeline so do not skip entirely.
FRIDAY Jun 5
Verification only. No new work. If something is not done by today it is too late to start.
13 | All slide decks confirmed in Canva and ready | LangChain (Days 2–3), Enterprise Adoption (Day 1), RAG-Based LLMs (Day 5 if included) — all final versions live in Canva. | Radhika | Jun 5 — all days | DO IT NEXT | Final confirmation pass. No editing on Friday — only confirming what was built Tuesday–Thursday is in place and correct.
14 | Everything closed — hand off to bootcamp week | No open items. All content, notebooks, and decks verified and ready going into the weekend before Jun 8. | Radhika | Jun 5 EOD | DO IT NEXT | Hard close. Bootcamp starts Monday Jun 8. The weekend is not prep time.
NEXT BOOTCAMP — Do not start before June 8
Deprioritised for this bootcamp. Do not add scope this week.
15 | Introduce DeepSeek in the final project | Add DeepSeek as an option in the Final Project (Day 5, Jun 12). Not needed for this bootcamp. Plan for the next offering. | TBD | Next bootcamp | DON'T DO IT NOW | From matrix. High effort, not time-critical for Jun 8 bootcamp. Starting this week adds scope risk with no benefit to the current offering.
PRIORITY QUADRANT KEY (from matrix)
DO IT NOW | High impact — resolve immediately. Blocks or risks other tasks.
DO IT NEXT | High impact, higher effort — execute once decisions are locked.
DO IT IF/WHEN THERE IS TIME | Lower priority — important but not blocking this bootcamp.
DON'T DO IT NOW | Next bootcamp — do not start before June 8.